## Apr
Village | No. of HH | SHGs formed | Water structures built | Farmers trained | Remarks
Wadgaon | 151 | 0 | 1 | 33
Otur | 219 | 2 | 1 | 16 | Data pending
Manchar | 95 | 1 | 0 | 15
Narayangaon | 163 | 2 | 2 | 26 | Data pending
Junnar | 124 | 0 | 0 | 27
Saswad | 192 | 1 | 1 | 23 | Monsoon delay
Baramati | 173 | 3 | 1 | 34 | On track
Maval | 89 | 2 | 0 | 29 | Monsoon delay
Indapur | 95 | 1 | 0 | 30 | Data pending
Shirur | 158 | 0 | 0 | 8 | Data pending
Rajgurunagar | 117 | 3 | 2 | 20
Purandar | 205 | 0 | 0 | 27
Ambegaon | 185 | 3 | 1 | 6
Velhe | 220 | 2 | 2 | 40
Shirval | 186 | 3 | 0 | 12
Khed | 184 | 2 | 1 | 22 | Target revised
TOTAL | 2556 | 25 | 12 | 368

## May
Village | No. of HH | SHGs formed | Water structures built | Farmers trained | Remarks
Wadgaon | 161 | 2 | 1 | 37 | Data pending
Otur | 223 | 0 | 1 | 5 | On track
Manchar | 107 | 2 | 1 | 37 | Monsoon delay
Narayangaon | 171 | 1 | 0 | 25 | Data pending
Junnar | 128 | 0 | 2 | 26 | Monsoon delay
Saswad | 207 | 2 | 1 | 13 | Target revised
Baramati | 177 | 0 | 0 | 8 | Monsoon delay
Maval | 98 | 2 | 1 | 40
Indapur | 97 | 3 | 1 | 23 | On track
Shirur | 158 | 2 | 2 | 38 | Target revised
Rajgurunagar | 127 | 3 | 0 | 19
Purandar | 212 | 1 | 1 | 17
Ambegaon | 196 | 2 | 2 | 22 | Target revised
Velhe | 232 | 0 | 1 | 12 | Target revised
Shirval | 201 | 3 | 2 | 26 | Target revised
Khed | 198 | 3 | 0 | 10 | Target revised
TOTAL | 2693 | 26 | 16 | 358

## Jun
Village | Households reached | SHGs formed | Water conservation structures | Farmers trained | Remarks
Wadgaon | 173 | 3 | 2 | 39 | Monsoon delay
Otur | 233 | 2 | 0 | 11 | Monsoon delay
Manchar | 109 | 0 | 1 | 7 | Monsoon delay
Narayangaon | 165 | 3 | 0 | 5
Junnar | 140 | 2 | 1 | 14 | Target revised
Saswad | 210 | 1 | 1 | 21
Baramati | 189 | 3 | 1 | 12 | On track
Maval | 93 | 0 | 0 | 19 | Target revised
Indapur | 111 | 2 | 2 | 29 | Monsoon delay
Shirur | 176 | 1 | 0 | 33 | Target revised
Rajgurunagar | 117 | 1 | 0 | 32 | Data pending
Purandar | 213 | 2 | 2 | 6
Ambegaon | 185 | 3 | 2 | 32 | On track
Velhe | 220 | 0 | 1 | 25 | On track
Shirval | 194 | 1 | 1 | 23 | Data pending
Khed | 196 | 2 | 0 | 9 | Monsoon delay
TOTAL | 2724 | 26 | 14 | 317

## Jul
Village | Households reached | New SHGs | Water conservation structures | Farmers trained | Remarks
Wadgaon | 166 | 0 | 0 | 29
Otur | 252 | 1 | 2 | 23
Manchar | 131 | 1 | 2 | 13
Narayangaon | 169 | 0 | 1 | 38
Junnar | 145 | 1 | 0 | 23
Saswad | 237 | 0 | 2 | 22
Baramati | 209 | 3 | 1 | 7
Maval | 119 | 2 | 2 | 7
Indapur | 140 | 3 | 2 | 16 | Data pending
Shirur | 191 | 3 | 2 | 22
Rajgurunagar | 126 | 3 | 1 | 30
Purandar | 223 | 1 | 1 | 5 | On track
Ambegaon | 194 | 2 | 1 | 14
Velhe | 235 | 2 | 1 | 24 | On track
Shirval | 210 | 2 | 2 | 11 | Monsoon delay
Khed | 223 | 3 | 0 | 11 | Monsoon delay
TOTAL | 2970 | 27 | 20 | 295

## Aug
Village | HH Covered | New SHGs | WC Structures | Farmers trained | Remarks
Wadgaon | 183 | 0 | 2 | 17 | Monsoon delay
Otur | 255 | 2 | 0 | 35 | On track
Manchar | 123 | 0 | 0 | 7 | Target revised
Narayangaon | 191 | 2 | 0 | 14 | Data pending
Junnar | 176 | 3 | 2 | 16 | Data pending
Saswad | 196 | 3 | 2 | 21
Baramati | 197 | 1 | 2 | 23 | Monsoon delay
Maval | 97 | 1 | 0 | 11 | Target revised
Indapur | 99 | 2 | 2 | 19 | Monsoon delay
Shirur | 214 | 1 | 1 | 16 | Target revised
Rajgurunagar | 153 | 0 | 0 | 33
Purandar | 233 | 2 | 0 | 17
Ambegaon | 197 | 3 | 1 | 17 | Data pending
Velhe | 276 | 1 | 2 | 32 | Data pending
Shirval | 206 | 3 | 2 | 12 | Target revised
Khed | 244 | 1 | 2 | 39 | Data pending
TOTAL | 3040 | 25 | 18 | 329

## Sep
Village | Households reached | SHGs formed (cumulative) | Water conservation structures | Farmers trained | Remarks
Wadgaon | 211 | 1 | 1 | 26 | On track
Otur | 249 | 0 | 1 | 12
Manchar | 105 | 0 | 1 | 25 | Monsoon delay
Narayangaon | 178 | 0 | 0 | 39
Junnar | 159 | 3 | 0 | 32 | On track
Saswad | 227 | 3 | 1 | 27 | On track
Baramati | 213 | 0 | 1 | 8 | On track
Maval | 149 | 2 | 1 | 27 | On track
Indapur | 160 | 0 | 0 | 19
Shirur | 193 | 2 | 2 | 24 | Monsoon delay
Rajgurunagar | 117 | 2 | 1 | 35 | On track
Purandar | 210 | 1 | 1 | 31 | On track
Ambegaon | 230 | 0 | 0 | 13 | Target revised
Velhe | 225 | 0 | 0 | 32
Shirval | 261 | 3 | 2 | 32
Khed | 234 | 0 | 2 | 29
TOTAL | 3121 | 17 | 14 | 411

## Consolidated
Village | Total HH Reached (Apr-Sep) | Total SHGs Formed | Total Water Structures | Total Farmers Trained
Wadgaon | 1045 | 6 | 7 | 181
Otur | 1431 | 7 | 5 | 102
Manchar | 670 | 4 | 5 | 104
Narayangaon | 1037 | 8 | 3 | 147
Junnar | 872 | 9 | 5 | 138
Saswad | 1269 | 10 | 8 | 127
Baramati | 1158 | 10 | 6 | 92
Maval | 645 | 9 | 4 | 133
Indapur | 702 | 11 | 7 | 136
Shirur | 1090 | 9 | 7 | 141
Rajgurunagar | 757 | 12 | 4 | 169
Purandar | 1296 | 7 | 5 | 103
Ambegaon | 1187 | 13 | 7 | 104
Velhe | 1408 | 5 | 7 | 165
Shirval | 1258 | 15 | 9 | 116
Khed | 1279 | 11 | 5 | 120

## Dashboard
Programme Dashboard (pasted from PivotTable)
Indicator | April | May | June | July | August | September
Households Reached | 2556 | 2693 | 2724 | 2970 | 3040 | 3121
SHGs Formed | 25 | 26 | 26 | 27 | 25 | 17
Water Structures | 12 | 16 | 14 | 20 | 18 | 14
Farmers Trained | 368 | 358 | 317 | 295 | 329 | 411