## Indicator Tracker
Indicator | Target | Achieved | % Achievement | Remarks
Students enrolled | 320 | 320 | 100 | Revised target under discussion
Students retained (no dropout) | 300 | 292 | 97.3 | Delay due to monsoon
Avg attendance % | 85 | 81 | 95.3 | Revised target under discussion
Students at 'Story' reading level | 60 | 54 | 90 | Data pending from field
Learning camps conducted | 12 | 11 | 91.7 | Revised target under discussion
Parent meetings held | 6 | 6 | 100 | Ahead of target
Teachers trained | 18 | 16 | 88.9 | Funder query pending
Classrooms with library corner | 14 | 12 | 85.7 | On track
Remedial sessions conducted | 40 | 47 | 117.5 | On track
Students receiving scholarship | 25 | 21 | 84 | Delay due to monsoon
School infrastructure audits | 8 | 8 | 100 | Funder query pending
Community awareness sessions | 10 | 7 | 70 | Revised target under discussion
TOTAL | 898 | 875 | 97.4